Action 6: Development and application of a two-way direct interaction process with stakeholders

The Project Manager has already officially informed all five stakeholders regarding the initiation of ACEPT-AIR project, as described in paragraph 4.1. He has also met several times with representatives of the Ministry of Environment, Energy and Climate Change, in order to discuss key issues and specific management needs in relation to the application of an integrated environmental policy for ambient air quality. In addition, AUTH and UTH have been in contact with the Municipality of Thessaloniki and the Regional Union of Magnesia and N. Sporades (former Prefecture of Magnesia), respectively.

The original plan to organize an informative meeting in the framework of the 3rd International Conference on Environmental Management, Engineering, Planning and Economics (CEMEPE, 19-24 June 2011, Skiathos Island) was cancelled due to limited participation from the stakeholders' part. The partners have discussed some initial issues with each stakeholder separately, and a new informative seminar is being planned for December 2011, at a more central location (Athens)

During the field measurement campaigns, NCSR “D” and AUTH have had the opportunity to meet and collaborate closely with the Ministry of Environment, Energy and Climate Change, the Coalition of 21 Local Authorities of North and East Athens and the Municipality of Thessaloniki. All three stakeholders assisted in site selection / preparation issues and were constantly held informed of the progress of the measurement campaigns. In addition, NCSR “D” has contacted the Coalition of 21 Local Authorities of North and East Athens to examine the possibility of organizing short-term measurements at a number of municipalities. There was increased interest by the part of the municipalities and Mobilab was employed in order to conduct measurement in as many sites as possible.

Moreover, the Project Manager has met several times with representatives of the Ministry of Environment, Energy and Climate Change, in order to discuss as well key issues and specific management needs in relation to the application of an integrated environmental policy for ambient air quality. These meetings have provided valuable material for the development of the Policy tool.